

|  |  |  |  |
| --- | --- | --- | --- |
| **PROJECT : Recovery Roading** | | | |
| **Project Owner : WDC** | | | |
| **Team : Transportation** | | | |
| **Interdependencies :** **Whakatāne District Recovery project plan workstreams – community, built environment, economic, WDC, BOPRC** | | | |
| **Tasks :** | **Milestone** | **Who** | **Progress** |
| Murupara to Waikaremoana | Early August | WDC | Work on Te Whaiti Rd. underway to open to local traffic in 3 weeks. 6 weeks to full public access |
| Troutbeck Road | June 12 start  June 30 finish | BOPRC – Tony Dunlop | Major 6-8m washout at north bridge abutment. Work being carried out currently. Design options have been assessed and a preferred option will be determined this week. Reinstatement works will be able to commence shortly thereafter, dependent on contractor availability. |
| Waimana Gorge | Mid July | NZTA | State Highway 2 through the Waimana Gorge remains closed as the contractor continues work to stabilise the slip site. Benched are being cut into the slip site to increase the stability of the land, and Engineers will be re-assessing progress to day. |
| Waimana Road West, Waimana | Early June |  | Temporary access has been provided across the breach in the road. Permanent repair work is underway and the road pavement with be completed this week weather permitting. |
| Galatea Road (below Matahina dam) | End of Dec-Jan 2018 | WDC | The road is useable but the site needs reassessment for long term stability. Real problem site with issues from river to road. |
| Get public transport routes up and running |  |  | Services are mostly running but some with restrictions |
| College Road, Edgecumbe | Jan-March 2018 | BOPRC – stopbank project | The single lane section past the stopbank repair has been widened to two lanes and sealed. A sealed footpath has also been constructed and is available for use. Full reconstruction will commence once stop bank has finished reconstruction in December. |
| Horomanga Bridge | End of July | WDC | Structural damage requires repair. There is a longer term project required for dealing with the river across the plains which needs to be assessed with BOPRC |
| Kopuriki Road/Lake Aniwaniwa | Dec? | NRER - Simon | Road needs reassessment where the breach occurred but this needs to be a project connected to Lake Aniwaniwa long term planning project currently underway. It’s a project for BOPRC and WDC to work on together |
| Galatea/Waiohau roading assessment project | Sept-Dec | WDC/BOPRC | There is a need for a overall assessment of the roading infrastructure across the Galatea/Waiohau plains to best develop long term resilience. But it needs to occur after some of the urgent work has been completed. |
| Lowe Road | End of Sept | WDC | Scouring of river along this road area which will need repair. Not urgent. |

A1158191